## Backlog
Issue Key | Issue Type | Summary | Epic Name | Description | Epic Link | Priority | Assignee | Story Points | Sprint | Labels | Requirements | Acceptance Criteria | Status
CFT-1 | Epic | File Compression | File Compression | Compress a selected file or folder with a supported lossless algorithm, without modifying the original, and report metrics. |  | High | Jai Jaswanth Tummala |  |  | f1 | REQ-001 to REQ-005 | Epic is done when all linked stories are Done. | To Do
CFT-2 | Epic | Huffman Compression Engine | Huffman Compression Engine | Huffman encoding with canonical codes and stored metadata; arbitrary bytes; empty and single-symbol inputs. |  | High | Jai Jaswanth Tummala |  |  | f2 | REQ-006 to REQ-010 | Epic is done when all linked stories are Done. | To Do
CFT-3 | Epic | File Decompression | File Decompression | Restore files and folders from tool-generated archives exactly, rejecting malformed input and protecting existing files. |  | High | Architha Sidharth Panicker |  |  | f3 | REQ-011 to REQ-015 | Epic is done when all linked stories are Done. | To Do
CFT-4 | Epic | Integrity Validation | Integrity Validation | Checksum and header validation so a corrupted archive is never reported as valid. |  | High | Architha Sidharth Panicker |  |  | f4 | REQ-016 to REQ-019 | Epic is done when all linked stories are Done. | To Do
CFT-5 | Epic | Algorithm Comparison | Algorithm Comparison | Compare at least two algorithms on identical input with consistent measurement; report failures separately. |  | High | Krati Patil |  |  | f5 | REQ-020 to REQ-023 | Epic is done when all linked stories are Done. | To Do
CFT-6 | Epic | Statistics and Reporting | Statistics and Reporting | Ratio and space-saved calculation, readable summaries and report export. |  | High | Krati Patil |  |  | f6 | REQ-024 to REQ-027 | Epic is done when all linked stories are Done. | To Do
CFT-7 | Epic | Batch Processing | Batch Processing | Process multiple files or a folder with per-item results and a summary; one failure never stops the batch. |  | High | Chandana Rajeswari P |  |  | f7 | REQ-028 to REQ-032 | Epic is done when all linked stories are Done. | To Do
CFT-8 | Epic | Operation History | Operation History | Local SQLite history of operations; created automatically; viewable in the application. |  | High | Chandana Rajeswari P |  |  | f8 | REQ-033 to REQ-036 | Epic is done when all linked stories are Done. | To Do
CFT-9 | Epic | Desktop Interface | Desktop Interface | Tkinter/ttk screens, background worker, progress and clear error feedback. |  | High | Architha Sidharth Panicker / all |  |  | f9 | SRS 3.1, NFR 6.1 | Epic is done when all linked stories are Done. | To Do
CFT-10 | Epic | Platform, CI, Quality and Documentation | Platform, CI, Quality and Documentation | Repository, CI, test infrastructure, fuzz/performance/cross-platform testing, traceability and documentation. |  | Medium | All |  |  | all | NFR 6.1 to 6.4 | Epic is done when all linked stories are Done. | To Do
CFT-11 | Task | Project skeleton and repository structure |  | Create src/cft (ui, services, core, infra), tests (unit, integration, system, data), pyproject.toml with Ruff and pytest settings, and a README with setup steps. | CFT-10 | Highest | Jai Jaswanth Tummala | 3 | Sprint 1 | setup | NFR 6.4 | Fresh clone installs and runs `pytest` green on an empty suite; `ruff check` passes; layer folders match the architecture document. | To Do
CFT-12 | Task | GitHub Actions CI: lint and tests on 3 OS x Python 3.12/3.13 |  | Workflow running Ruff and pytest on ubuntu, windows and macos for Python 3.12 and 3.13; Linux job installs xvfb for GUI tests. | CFT-10 | Highest | Architha Sidharth Panicker | 5 | Sprint 1 | ci | NFR 6.4 | Every push and PR triggers the matrix; failing test turns the run red; run time under 10 minutes for the current suite. | To Do
CFT-13 | Story | CompressionAlgorithm interface and AlgorithmRegistry |  | As a developer I want one algorithm interface and a registry so that new algorithms plug in without changing the GUI. | CFT-1 | Highest | Jai Jaswanth Tummala | 3 | Sprint 1 | core F1 | REQ-003, REQ-020 | Interface defines build_metadata, compress, decompress, algorithm_id and name; registry registers, lists and gets by name; unknown name raises UnsupportedAlgorithmError; a dummy algorithm can be registered in a test. | To Do
CFT-14 | Story | Archive container: 64-byte header reader and writer |  | As a developer I want a fixed header (magic, version, algorithm id, sizes, SHA-256, metadata length, CRC32) so that archives can be validated before decoding. | CFT-3 | Highest | Architha Sidharth Panicker | 5 | Sprint 1 | core F3 | REQ-008, REQ-012, REQ-018 | Header round-trips; wrong magic, version, CRC or short header raise ArchiveFormatError; file size must equal 64 + metadata + payload; layout matches Section 6.1 of the architecture. | To Do
CFT-15 | Story | PathValidator: input checks and safe_join |  | As a user I want invalid inputs rejected clearly so that I know what to fix. | CFT-1 | Highest | Jai Jaswanth Tummala | 3 | Sprint 1 | core F1 security | REQ-001, REQ-002, NFR 6.3 | Existing file/folder accepted; missing, unreadable, special-file and broken-symlink inputs rejected with specific messages; safe_join rejects absolute paths, drive letters, '..' and NUL. | To Do
CFT-16 | Story | SQLite schema and repository bootstrap |  | As a user I want the history database created automatically so that the app starts on first run. | CFT-8 | High | Chandana Rajeswari P | 3 | Sprint 1 | core F8 | REQ-033, REQ-036 | Missing or empty DB file gets the operation_history table and index; app startup does not fail; schema matches the Field Layouts workbook. | To Do
CFT-17 | Story | Metrics: compression ratio and space saved |  | As a user I want accurate ratio and space-saved figures so that I can judge compression. | CFT-6 | High | Krati Patil | 2 | Sprint 1 | core F6 | REQ-025, REQ-026 | ratio = compressed/original; saved % = (original-compressed)/original*100; expansion gives ratio above 1 and negative saved %; 0-byte original returns N/A without exceptions. | To Do
CFT-18 | Task | Test fixtures and edge-case data generator |  | Seeded generators for empty, 1-byte, single-symbol, all-bytes, random, repetitive and nested-folder data, plus corrupt and traversal archive builders. | CFT-10 | High | Krati Patil | 3 | Sprint 1 | testing | NFR 6.4 | Fixtures are deterministic and available to all tests; large files are generated at test time, not committed; data sets match Section 6.2 of the Test Plan. | To Do
CFT-19 | Story | UI shell: main window with navigation |  | As a user I want a main screen with Compress, Decompress, Compare, Batch, History and Help so that features are easy to find. | CFT-9 | High | Chandana Rajeswari P | 3 | Sprint 1 | ui F9 | SRS 3.1 | Window opens on all three OS; each navigation entry shows its placeholder view; no business logic in view classes. | To Do
CFT-20 | Story | Huffman: chunked frequency counting |  | As a developer I want symbol frequencies computed from a stream so that large files need little memory. | CFT-2 | High | Jai Jaswanth Tummala | 2 | Sprint 2 | core F2 | REQ-006 | Frequency table for b'aabbbc' is {a:2,b:3,c:1}; chunked and single-pass results are identical for a 5 MB input. | To Do
CFT-21 | Story | Huffman: canonical prefix-free codes with deterministic ties |  | As a developer I want deterministic prefix-free codes so that output is reproducible. | CFT-2 | Highest | Jai Jaswanth Tummala | 5 | Sprint 2 | core F2 | REQ-007 | No code is a prefix of another (property test); more frequent symbols never get longer codes; same input gives byte-identical output. | To Do
CFT-22 | Story | Huffman: code-length metadata serialisation |  | As a developer I want the code table stored compactly so that the decoder can rebuild it from the archive alone. | CFT-2 | High | Jai Jaswanth Tummala | 3 | Sprint 2 | core F2 | REQ-008 | 256-byte code-length block written and read back; decoder restores data using only the metadata. | To Do
CFT-23 | Story | Huffman: encode and decode arbitrary bytes |  | As a user I want any file type compressed so that binary files work. | CFT-2 | Highest | Jai Jaswanth Tummala | 5 | Sprint 2 | core F2 | REQ-009 | All 256 byte values and 1 MB random data round-trip exactly; final partial byte handled correctly. | To Do
CFT-24 | Story | Huffman: empty and single-symbol inputs |  | As a user I want edge-case files handled so that nothing crashes or corrupts. | CFT-2 | High | Jai Jaswanth Tummala | 3 | Sprint 2 | core F2 | REQ-010 | Empty file, one-byte file, single repeated symbol and two-symbol inputs round-trip; single symbol uses the 1-bit code rule. | To Do
CFT-25 | Story | RLE codec |  | As a user I want a second algorithm so that comparison is meaningful. | CFT-5 | Medium | Krati Patil | 3 | Sprint 2 | core F5 | REQ-020 | (count 1-255, value) pairs; round-trips binary data and runs longer than 255; registered in the registry. | To Do
CFT-26 | Story | LZW codec (9-12 bit codes, dictionary reset) |  | As a user I want a dictionary-based algorithm so that I can compare it with Huffman and RLE. | CFT-5 | Medium | Chandana Rajeswari P | 5 | Sprint 2 | core F5 | REQ-020 | Round-trips text, binary and repetitive data; CLEAR/EOF codes handled; dictionary resets when full; registered in the registry. | To Do
CFT-27 | Story | Compression service: single file without touching the original |  | As a user I want my original file left unchanged so that compression is safe. | CFT-1 | Highest | Jai Jaswanth Tummala | 5 | Sprint 2 | service F1 | REQ-001, REQ-003, REQ-004 | Archive created through temp file and atomic rename; source hash and mtime unchanged; output path equal to input path refused; chosen algorithm id is in the header. | To Do
CFT-28 | Story | Folder compression via container stream |  | As a user I want to compress a whole folder so that I get one archive. | CFT-1 | High | Jai Jaswanth Tummala | 5 | Sprint 2 | service F1 | REQ-001 | Nested folders, empty subfolders and unicode names are stored with relative paths; symlinks are reported as unsupported. | To Do
CFT-29 | Story | Compression result: sizes, ratio, space saved, elapsed time |  | As a user I want to see how well compression worked. | CFT-1 | High | Jai Jaswanth Tummala | 2 | Sprint 2 | service F1 | REQ-005 | OpResult contains original size, compressed size, ratio, space saved and elapsed ms matching independent calculation. | To Do
CFT-30 | Story | SHA-256 checksum stored in the archive header |  | As a user I want an integrity digest stored so that corruption can be detected. | CFT-4 | Highest | Architha Sidharth Panicker | 3 | Sprint 2 | core F4 | REQ-016 | Digest equals hashlib.sha256 of the container stream; computed while streaming; shown as 64 hex characters. | To Do
CFT-31 | Story | Decompression service: dispatch by algorithm id and restore bytes |  | As a user I want to restore my files exactly. | CFT-3 | Highest | Architha Sidharth Panicker | 5 | Sprint 2 | service F3 | REQ-011, REQ-013 | Round trip for each algorithm gives byte-identical files and folders; temp output used until verification passes. | To Do
CFT-32 | Story | Reject malformed or unsupported archives |  | As a user I want a clear error for bad archives instead of garbage output. | CFT-3 | Highest | Architha Sidharth Panicker | 5 | Sprint 2 | service F3 | REQ-012 | Non-archives, truncated headers/payloads, unknown versions and algorithm ids give distinct messages; no output left on disk. | To Do
CFT-33 | Story | History repository: insert and query |  | As a user I want every operation recorded so that I can review it later. | CFT-8 | High | Chandana Rajeswari P | 3 | Sprint 2 | core F8 | REQ-033, REQ-034 | Parameterised inserts; lengths clipped to 255/1024/500; mandatory fields always set; SQL metacharacters in names are stored as data; file content never stored. | To Do
CFT-34 | Story | Overwrite confirmation and atomic write |  | As a user I want to be asked before an existing file is replaced. | CFT-3 | High | Architha Sidharth Panicker | 3 | Sprint 3 | service F3 | REQ-014 | Existing destination raises DestinationExistsError; decline leaves file untouched; confirm replaces via temp file and os.replace. | To Do
CFT-35 | Story | Decompression result reporting |  | As a user I want to know where files were restored. | CFT-3 | Medium | Architha Sidharth Panicker | 2 | Sprint 3 | service F3 | REQ-015 | Result includes destination path, restored size and validation status. | To Do
CFT-36 | Story | Folder extraction with path-traversal protection |  | As a user I want extraction to be safe even for hostile archives. | CFT-3 | Highest | Architha Sidharth Panicker | 5 | Sprint 3 | service F3 security | NFR 6.3 | Entries with '../', absolute, drive-letter or backslash tricks are rejected; nothing written outside the destination; symlinks never created. | To Do
CFT-37 | Story | Checksum mismatch detection and never-success rule |  | As a user I want corrupted archives reported as invalid. | CFT-4 | Highest | Architha Sidharth Panicker | 5 | Sprint 3 | service F4 | REQ-017, REQ-019 | Bit flip or altered digest gives INVALID; temp output deleted; history status INVALID; no success message; fuzz cases never pass. | To Do
CFT-38 | Story | Header and metadata consistency checks |  | As a user I want inconsistent archives detected before decoding. | CFT-4 | High | Architha Sidharth Panicker | 3 | Sprint 3 | service F4 | REQ-018 | Bad magic, CRC, algorithm id and declared-size mismatch are detected and reported as INVALID. | To Do
CFT-39 | Story | Comparison service with per-algorithm failure isolation |  | As a user I want to compare algorithms on my file. | CFT-5 | High | Krati Patil | 5 | Sprint 3 | service F5 | REQ-020, REQ-021, REQ-022, REQ-023 | At least two algorithms required; identical input for each; per-algorithm metrics returned; a failing algorithm is listed as FAILED while others still report. | To Do
CFT-40 | Story | Consistent timing harness |  | As a user I want fair timing figures. | CFT-5 | Medium | Krati Patil | 3 | Sprint 3 | core F5 | REQ-021, REQ-022 | Uses time.perf_counter, sequential runs, counting null sink instead of disk; clock injectable for tests. | To Do
CFT-41 | Story | Statistics summary view |  | As a user I want a readable summary of operations. | CFT-6 | Medium | Krati Patil | 3 | Sprint 3 | ui F6 | REQ-024 | Table shows type, source, algorithm, sizes, ratio, saved %, time and status; N/A shown for zero-size inputs. | To Do
CFT-42 | Story | Report export (CSV and TXT) |  | As a user I want to export results. | CFT-6 | Medium | Krati Patil | 3 | Sprint 3 | service F6 | REQ-027 | Compression and comparison reports contain exactly the Field Layouts report fields; unwritable target gives a clear error and no partial file. | To Do
CFT-43 | Story | Batch service: queue, per-item results, failure isolation |  | As a user I want to process many files at once and keep going if one fails. | CFT-7 | High | Chandana Rajeswari P | 8 | Sprint 3 | service F7 | REQ-028, REQ-029, REQ-030, REQ-031 | Files or folder expanded; no valid item skipped; per-item SUCCESS/FAILED with reason; existing destination marked FAILED, not overwritten; same-named files in different folders do not collide. | To Do
CFT-44 | Story | Batch summary and counts |  | As a user I want a summary of the batch. | CFT-7 | High | Chandana Rajeswari P | 3 | Sprint 3 | service F7 | REQ-032 | processed = successful + failed for all-success, all-failed and mixed batches; empty selection gives a message and no history row. | To Do
CFT-45 | Story | History view: list, newest first, filter |  | As a user I want to browse past operations. | CFT-8 | Medium | Chandana Rajeswari P | 3 | Sprint 3 | ui F8 | REQ-035 | Records shown newest first; filter by operation type; survives app restart. | To Do
CFT-46 | Story | TaskRunner: worker thread, queues, progress and cancel |  | As a user I want the window to stay responsive during long operations. | CFT-9 | Highest | Krati Patil | 5 | Sprint 3 | ui F9 performance | NFR 6.1 | Tasks run off the UI thread; progress events are monotonic; cancel stops between chunks and removes temp files; Tk heartbeat gap stays below 200 ms in the 100 MB test. | To Do
CFT-47 | Story | Compress screen |  | As a user I want to pick a file or folder, an algorithm and a destination, and see results. | CFT-9 | High | Jai Jaswanth Tummala | 5 | Sprint 3 | ui F9 | REQ-001, REQ-003, REQ-005 | File/folder dialogs; algorithm list built from the registry; progress bar; results panel with the five metrics; clear error dialogs. | To Do
CFT-48 | Story | Decompress screen with overwrite dialog |  | As a user I want to restore archives from the GUI. | CFT-9 | High | Architha Sidharth Panicker | 3 | Sprint 3 | ui F9 | REQ-011, REQ-014, REQ-015 | Archive picker; destination chooser; overwrite confirmation dialog; success shows destination; invalid archive shows an error, not success. | To Do
CFT-49 | Story | Compare screen |  | As a user I want to run a comparison from the GUI. | CFT-9 | Medium | Krati Patil | 3 | Sprint 4 | ui F9 | REQ-020, REQ-022, REQ-023 | Select at least two algorithms; results table; failed runs shown in a separate section. | To Do
CFT-50 | Story | Batch screen |  | As a user I want to run batches from the GUI. | CFT-9 | Medium | Chandana Rajeswari P | 3 | Sprint 4 | ui F9 | REQ-028, REQ-032 | Multi-file and folder selection; live per-item status; summary dialog at the end. | To Do
CFT-51 | Story | Error-message catalogue and dialogs |  | As a user I want errors that say what failed and what to do. | CFT-9 | Medium | Chandana Rajeswari P | 3 | Sprint 4 | ui F9 usability | NFR 6.4 | One catalogue maps every CftError subclass to a message; no stack traces shown; usability checklist (TC-072) passes. | To Do
CFT-52 | Story | Disk-full and permission failure handling with cleanup |  | As a user I want failures to leave no half-written files and no false success. | CFT-1 | High | Jai Jaswanth Tummala | 3 | Sprint 4 | service F1 safety | NFR 6.2 | Simulated ENOSPC and permission errors give StorageError, remove temp output and record FAILED. | To Do
CFT-53 | Story | Corrupt or locked history database fallback |  | As a user I want the app to keep working if history breaks. | CFT-8 | Medium | Chandana Rajeswari P | 2 | Sprint 4 | core F8 | REQ-036 | Corrupt or locked DB shows one warning; compression and decompression still work; history disabled for the session. | To Do
CFT-54 | Task | Fuzz and property tests with Hypothesis |  | Round-trip properties for all algorithms and mutation fuzzing of archives. | CFT-10 | High | Architha Sidharth Panicker | 5 | Sprint 4 | testing | REQ-013, REQ-017, REQ-018, REQ-019 | Round-trip property passes for all registered algorithms; 500 mutated archives never reported valid unless identical; seeds fixed in CI. | To Do
CFT-55 | Task | Performance and memory baselines |  | Measure speed and peak memory for 10 MB and 100 MB inputs on the reference laptop; freeze thresholds. | CFT-10 | Medium | Krati Patil | 3 | Sprint 4 | testing performance | NFR 6.1 | Baseline table committed; peak memory within the agreed ceiling; findings logged as issues if exceeded. | To Do
CFT-56 | Task | Coverage gate and static analysis in CI |  | Enforce coverage targets and Ruff in CI; add dependency-rule check (core imports nothing from ui/infra). | CFT-10 | Medium | Architha Sidharth Panicker | 2 | Sprint 4 | ci | NFR 6.4 | CI fails below 80% overall, 90% core, 85% services/infra; import rule test passes. | To Do
CFT-57 | Task | Cross-platform smoke test (Windows, Linux, macOS) |  | Run ST-01, ST-04 and ST-10 manually on all three systems and record results. | CFT-10 | High | Chandana Rajeswari P | 3 | Sprint 4 | testing | NFR 6.4 | Same behaviour on all three; platform issues logged and fixed or documented. | To Do
CFT-58 | Task | Execute system tests ST-01 to ST-16 and log defects |  | Formal system test run and regression, with a test summary report. | CFT-10 | Highest | Krati Patil | 5 | Sprint 4 | testing | All REQ | All STs executed and recorded; defects logged as GitHub issues; summary report committed; exit criteria evaluated. | To Do
CFT-59 | Task | Update RTM with code and test references |  | Replace TBD entries in SRS Appendix C with real code files and TC/ST IDs. | CFT-10 | High | Krati Patil | 2 | Sprint 4 | docs | All REQ | All 36 rows have code file, TC and ST references; matrix reviewed by the team. | To Do
CFT-60 | Task | README, user guide and Help screen content |  | Document install, usage, archive format notes and known limits (timestamps and permissions not preserved). | CFT-10 | Medium | Chandana Rajeswari P | 3 | Sprint 4 | docs | SRS 3.1 | README and Help screen describe all screens; limits listed; steps verified on a clean machine. | To Do
CFT-61 | Task | Final report and demo script |  | Compile final report and rehearse the demonstration. | CFT-10 | High | Krati Patil | 3 | Sprint 4 | docs | All | Report and demo script complete; demo run end to end without errors. | To Do

## Epics
Epic Key | Epic | Feature | Owner | Requirements | Stories and tasks | Story points | Share of total points
CFT-1 | File Compression | F1 | Jai Jaswanth Tummala | REQ-001 to REQ-005 | 6 | 21 | 11.48%
CFT-2 | Huffman Compression Engine | F2 | Jai Jaswanth Tummala | REQ-006 to REQ-010 | 5 | 18 | 9.836%
CFT-3 | File Decompression | F3 | Architha Sidharth Panicker | REQ-011 to REQ-015 | 6 | 25 | 13.66%
CFT-4 | Integrity Validation | F4 | Architha Sidharth Panicker | REQ-016 to REQ-019 | 3 | 11 | 6.011%
CFT-5 | Algorithm Comparison | F5 | Krati Patil | REQ-020 to REQ-023 | 4 | 16 | 8.743%
CFT-6 | Statistics and Reporting | F6 | Krati Patil | REQ-024 to REQ-027 | 3 | 8 | 4.372%
CFT-7 | Batch Processing | F7 | Chandana Rajeswari P | REQ-028 to REQ-032 | 2 | 11 | 6.011%
CFT-8 | Operation History | F8 | Chandana Rajeswari P | REQ-033 to REQ-036 | 4 | 11 | 6.011%
CFT-9 | Desktop Interface | F9 | Architha Sidharth Panicker / all | SRS 3.1, NFR 6.1 | 7 | 25 | 13.66%
CFT-10 | Platform, CI, Quality and Documentation | All | All | NFR 6.1 to 6.4 | 11 | 37 | 20.22%
Total |  |  |  |  | 51 | 183 | 100%

## Sprint Plan
Sprint plan and workload
Sprint | Goal | Stories and tasks | Story points | Share of total | Load vs average
Sprint 1 | Foundation: repo, CI, interfaces, container header, path rules, schema, metrics, fixtures, UI shell. | 9 | 30 | 16.39% | 65.57%
Sprint 2 | Core engines: Huffman, RLE, LZW; compression and decompression services; checksum; history repository. | 14 | 54 | 29.51% | 118%
Sprint 3 | Features and UI: integrity rules, comparison, statistics, batch and history services, background worker, Compress/Decompress/Statistics/History screens. | 15 | 59 | 32.24% | 129%
Sprint 4 | Hardening and release: Compare and Batch screens, failure handling, fuzz, performance, cross-platform, system tests, RTM, documentation. | 13 | 40 | 21.86% | 87.43%
Total |  | 51 | 183 | 100%
Story points by assignee and sprint
Assignee | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Total | Share of total
Jai Jaswanth Tummala | 9 | 30 | 5 | 3 | 47 | 25.68%
Architha Sidharth Panicker | 10 | 13 | 21 | 7 | 51 | 27.87%
Krati Patil | 5 | 3 | 19 | 16 | 43 | 23.5%
Chandana Rajeswari P | 6 | 8 | 14 | 14 | 42 | 22.95%
Total | 30 | 54 | 59 | 40 | 183 | 100%
Check: total points by assignee equals total points by sprint | OK
Assumptions
Sprint length and calendar dates are not fixed yet; set them in Jira once the course calendar is confirmed.
Story points are relative (Fibonacci scale 1-2-3-5-8). Velocity is unknown: after Sprint 1 compare actual points done with the plan and move stories between Sprint 3 and Sprint 4 if needed.
Sprint 3 was the heaviest sprint, so the Compare and Batch screens (CFT-49, CFT-50) are planned in Sprint 4; they only need the services built in Sprint 3. If velocity is still low, CFT-41 (statistics view) can follow them.
Assignees follow the ownership in the proposal; TaskRunner (CFT-46), RLE (CFT-25), LZW (CFT-26) and the RTM/report tasks are shared to balance load.
Load per person is uneven by sprint: Jai peaks in Sprint 2 (Huffman engine and services), Krati peaks in Sprint 3 and Chandana in Sprints 3-4. Pair on Huffman stories (CFT-21, CFT-23) if Jai falls behind.

## Read Me
Team 22 - Ctrl Freaks ¦ Project 76 - File Compression Tool ¦ Jira Backlog
Purpose | Product backlog for the File Compression Tool: 10 epics (one per feature F1-F9 plus platform/quality) and 51 stories/tasks, estimated, prioritised, assigned and planned over 4 sprints. Every story lists the SRS requirements it satisfies.
Sheets | Backlog = importable issue list. Epics = story counts and points per epic (formulas). Sprint Plan = points per sprint and per member (formulas).
Importing into Jira | 1) Create the project. 2) Import the Backlog sheet as CSV (File > Save as CSV). 3) Map columns: Summary, Issue Type, Description, Priority, Assignee, Labels, Story Points (Story point estimate), Sprint. 4) Epic rows use Epic Name; stories link through Epic Link (company-managed projects) or Parent (team-managed projects). 5) Assignees must be matched to Jira user accounts. Issue Key values here are planning IDs; Jira assigns the real keys on import, so re-link references if they differ.
Workflow | To Do > In Progress > In Review > Ready for Test > Done. Bugs found in testing are logged as GitHub issues linked to the story and the TC/ST ID.
Definition of Ready | Story has a requirement reference, acceptance criteria, an estimate and an assignee; dependencies are Done or in the same sprint.
Definition of Done | Code merged by pull request with one review from the paired member; unit and integration tests for the story written with REQ markers and passing; CI green on all three OS; acceptance criteria demonstrated; documentation updated; no open Critical or High defects on the story.
Estimation | Story points use the Fibonacci scale (1, 2, 3, 5, 8). 8 is the largest item (CFT-43); anything bigger should be split.
Priority | Highest = blocks other work or protects data correctness; High = required feature; Medium = required but not blocking; Low = nice to have.
Traceability | Requirements column links to SRS REQ IDs; test coverage for each REQ is in 22_Project Test Plan (TC and ST IDs); architecture references are in 22_SW Architecture.